## Sheet1
Will Assure Point To Be Done And Discuss Points
Srno. | Points Name | Status | Point Duration
1 | Identity Proof once entered that particular identity proof will be used through out the form | Pending | 30 min
2 | Executor Dynamic submission of alternate executor causes problem on submission | Pending | 30 min
3 | Two Witness Mandatory cannot be further proceed | Pending | 30 min
4 | Mapping of alternate beneficiary Proportion in both quick and detailed | Pending | 2-3 hour
5 | In Quick Will Document Confirmation Screen After Mapping | Pending | 2 hours
6 | In Codocil link for the add witness (Mandatory 2) | Pending | 30 min
7 | In Quick Will Mapping Fixing of records that are not displayed properly (for multiple records) | Pending | 20 min
8 | Individual firm same fields as that on register company | Pending | 30 min
9 | Document allotment error on submit fixing | Pending | 20 min
10 | Make a Payment Screen Where Discount Coupon will be asked and discounted amount can be seen while making payment | Pending | 3 hour
11 | on Distributor Login if testator Is created by distributor than distibutor can set the amount of that document | Pending | 2 hour
12 | In SuperAdmin - testator list there will be option of document column for Will,POA,Codocil,GiftDeeds,Livingwill where he can select document of his choice | Pending | 3 hour
13 | In SuperAdmin - when Document linked is clicked there will be two drop down for filter of the document for testator and distributor so according to the filter admin can make pdf and view document | Pending | 30 min
14 | Testator Should Update His all Details Before Proceeding to further steps | Completed | 20 min
note | The following points have been discussed with issued point during demo if any changes let us know |  | Till wed - thru